## WBS (2)
Crital Path | Task # Lv 12 | Task # Lv 2 | Task # Lv 3 | Task | Description | Key Deliverable | Planed Start Date | Planed End Date | Acutal Start Date | Action End Date | Progress % | RAG | Remark | PCA PIC | Vendor PIC | Sign-off (Y/N) | Sign-off by | Note | Jira Key | 欄1
Y | 1 | 0 | 0 | Project Initiation & Governance 專案啟動與治理
| 1 | 1 | 0 | Scope definition & boundary clarification 範圍定義與邊界釐清 | Define scope in/out, assumptions, dependencies, and exclusions. | Scope Statement | 2025-12-01 | 2025-12-15 |  |  | 100% |  |  | Kathy
| 1 | 2 | 0 | Stakeholder identification & RACI establishment 利益相關者識別與RACI權責建立 | Identify stakeholders; define roles/responsibilities and decision rights. | Stakeholder Map, RACI | 2026-01-10 | 2026-01-31 |  |  | 100% |  |  | Kathy
| 1 | 3 | 0 | Regulatory/compliance/security baseline review 法規/合規/安全基準審查 | Review applicable regulations, compliance obligations, and security baselines. | Compliance & Security Baseline | 2026-03-01 | 2026-04-30 |  |  | 100% |  |  | Kathy
| 2 | 0 | 0 | Requirements Management 需求管理
| 2 | 1 | 0 | 需求訪談(遠距投保+多媒體行銷+名單)
| 2 | 1 | 1 | 遠距投保 |  |  | 2025-12-22 | 2026-01-07 |  |  | 100% |  |  | Kathy
| 2 | 1 | 2 | 遠距照會(ePOS流程啟動) |  |  | 2026-01-08 | 2026-01-12 |  |  | 100% |  |  | Kathy
| 2 | 1 | 3 | 遠距優化項目說明與Prototype規劃 |  |  | 2026-01-28 | 2026-01-30 |  |  | 100% |  |  | Kathy
| 2 | 1 | 4 | 多媒體行銷(一般功能-布告欄/便條紙, 管理功能-組織管理/人事管理) |  |  | 2026-01-13 | 2026-01-15 |  |  | 100% |  |  | Kathy
| 2 | 1 | 5 | 多媒體行銷(銷售功能-業務人員功能 名單查詢 電話招攬 視訊招攬 與銷售追蹤) |  |  | 2026-01-16 | 2026-01-20 |  |  | 100% |  |  | Kathy
| 2 | 1 | 6 | 多媒體行銷(名單匯入作業與分派流程) |  |  | 2026-01-21 | 2026-01-22 |  |  | 100% |  |  | Kathy
| 2 | 1 | 7 | 多媒體行銷(主管管理功能-視訊會議室查看/VFA狀態/名單狀態) |  |  | 2026-01-23 | 2026-01-26 |  |  | 100% |  |  | Kathy
| 2 | 1 | 8 | 多媒體行銷(名單收回與名單合規匯入分派流程規劃) |  |  | 2026-01-27 | 2026-01-29 |  |  | 100% |  |  | Kathy
| 2 | 1 | 9 | 多媒體行銷(報表整合) |  |  | 2026-01-30 | 2026-01-30 |  |  | 100% |  |  | Kathy
| 2 | 1 | 10 | 多媒體行銷Prototype規劃 |  |  | 2026-02-20 | 2026-02-26 |  |  | 100% |  |  | Kathy
| 2 | 1 | 11 | 多媒體行銷workshop |  |  | 2026-05-15 | 2026-05-22 |  |  | 100% |  |  | Kathy
Y | 2 | 2 | 0 | BRD確認sign off |  |  | 2026-05-25 | 2026-05-29 |  |  | 100% |  |  | Linda
Y | 2 | 3 | 0 | FRS*73 sign off |  |  | 2026-06-01 | 2026-07-15 |  |  | 100% |  |  | Linda
| 2 | 4 | 0 | Non-Functional需求 sign off | Prepare technical docs and runbooks. | Tech Docs | 2026-06-15 | 2026-08-21 |  |  | 70% |  |  | YuChung | Wistron-Ned |  |  |  | MRSS-216
| 2 | 5 | 0 | 系統整合需求*17 sign off |  |  | 2026-06-15 | 2026-08-28 |  |  | 50% |  |  | YuChung | Wistron-Ned |  |  |  | MRSS-217
| 2 | 6 | 0 | 主約採購完成與合約簽署 |  |  | 2026-03-29 | 2026-05-29 |  |  | 100% |  |  | Dabin
| 2 | 7 | 0 | ID&V採購完成與合約簽署 |  |  | 2026-05-29 | 2026-09-30 |  |  | 30% |  |  | Kathy |  |  |  |  | MRSS-198
| 2 | 8 | 0 | CTI採購完成與合約簽署 |  |  | 2026-05-29 | 2026-09-30 |  |  | 30% |  |  | Kathy |  |  |  |  | MRSS-199
| 2 | 9 | 0 | BIA |  |  | 2026-07-27 | 2026-08-31 |  |  | 70% |  |  | Kathy |  |  |  |  | VFA2-44
| 3 | 0 | 0 | Architecture & Design 架構與設計
Y | 3 | 1 | 0 | 方案選型
| 3 | 1 | 1 | 視訊與錄影方案 |  |  | 2026-02-03 | 2026-02-20 |  |  | 100% |  |  | YuChung
| 3 | 1 | 2 | Webcall方案 |  |  | 2026-02-03 | 2026-02-20 |  |  | 100% |  |  | YuChung
| 3 | 1 | 3 | CTI系統整合 |  |  | 2026-07-06 | 2026-08-31 |  |  | 50% |  |  | YuChung |  |  |  |  | MRSS-219
| 3 | 1 | 4 | eKYC系統整合 |  |  | 2026-07-06 | 2026-08-31 |  |  | 70% |  |  | YuChung
| 3 | 2 | 0 | 系統架構
| 3 | 2 | 1 | 應用端架構 |  |  | 2026-04-20 | 2026-05-29 |  |  | 100% |  |  | YuChung | Wistron-Ned
| 3 | 2 | 2 | 雲端架構 |  |  | 2026-04-20 | 2026-05-29 |  |  | 100% |  |  | YuChung
| 3 | 2 | 3 | Architecture Principle and Design Standard |  |  | 2026-07-06 | 2026-08-21 |  |  | 100% |  |  | YuChung | Wistron-Ned |  |  |  | VFA2-45
| 3 | 2 | 4 | Technical Spec |  |  | 2026-08-03 | 2026-08-28 |  |  | 50% |  |  | YuChung | Wistron-Ned |  |  |  | MRSS-218
| 3 | 2 | 5 | Design check point | LLD deep dive meeting Get foundation approval Get GISP approval |  | 2026-06-01 | 2026-08-28 |  |  | 20% |  |  | YuChung
| 3 | 2 | 6 | Low-level Design Document |  |  | 2026-08-31 | 2026-09-18 |  |  | 0% |  |  | YuChung
Y | 3 | 3 | 0 | GSRC
| 3 | 3 | 1 | GSRC process-fill out forms |  |  | 2026-06-01 | 2026-08-28 |  |  | 70% |  |  | YuChung |  |  |  |  | MRSS-187
| 3 | 3 | 2 | GSRC process-registered |  |  | 2026-07-01 | 2026-08-28 |  |  | 0% |  |  | YuChung |  |  |  |  | MRSS-187
| 3 | 3 | 3 | GSRC process-Presentation |  |  | 2026-08-31 | 2026-09-11 |  |  | 0% |  |  | YuChung
| 3 | 3 | 4 | GSRC process-Get approval |  |  | 2026-08-31 | 2026-10-09 |  |  | 0% |  |  | YuChung
Y | 3 | 4 | 0 | AIWG (for ID&V)
| 3 | 4 | 1 | AIWG process-registered |  |  | 2026-08-03 | 2026-09-18 |  |  | 0% |  |  | Eddie
| 3 | 4 | 2 | AIWG process-fill out forms |  |  | 2026-08-03 | 2026-09-18 |  |  | 0% |  |  | Eddie
| 3 | 4 | 3 | AIWG process-evaluation |  |  | 2026-08-03 | 2026-10-13 |  |  | 0% |  |  | Eddie
| 3 | 4 | 4 | AIWG demo |  |  | 2026-11-01 | 2026-11-30 |  |  | 0% |  |  | Eddie
| 3 | 4 | 5 | AIWG process-submit |  |  | 2026-11-01 | 2026-11-30 |  |  | 0% |  |  | Eddie
| 3 | 5 | 0 | 安全管理評估
| 3 | 5 | 1 | 雲端安全管理評估表 |  |  | 2026-08-10 | 2026-09-30 |  |  | 0% |  |  | Kathy
| 3 | 5 | 2 | 雲端服務管理作業 |  |  | 2026-08-10 | 2026-09-30 |  |  | 0% |  |  | Kathy
| 4 | 0 | 0 | Environment Build & Setup 環境建置與設定 | Environment Build includes DEV/TEST/UAT/STG/PROD plus security baseline, monitoring, and validation evidence.
| 4 | 1 | 0 | Infrastructure provisioning 基礎設定配置 | Provision DEV/TEST/UAT/STG/PROD infrastructure and resources. | Provisioned Environments | 2026-05-04 | 2026-05-22 |  |  | 100% |  |  | YuChung
Y | 4 | 2 | 0 | Testing environment provisioning 測試環境配置 | Provision testing environment for SIT. | TEST/SIT Environment | 2026-05-04 | 2026-07-31 |  |  | 100% |  |  | YuChung
Y | 4 | 3 | 0 | 雲端環境確認 |  |  | 2026-05-04 | 2026-06-12 |  |  | 100% |  |  | YuChung
| 4 | 4 | 0 | Jfrog設置 |  |  | 2026-08-10 | 2026-08-28 |  |  | 0% |  |  | YuChung |  |  |  |  | MRSS-223
| 4 | 5 | 0 | 專案團隊人員權限申請 |  |  | 2026-08-10 | 2026-08-28 |  |  | 0% |  |  | YuChung |  |  |  |  | MRSS-223
| 4 | 6 | 0 | Staging/UAT environment provisioning 暫存/使用者驗收環境配置 | Provision UAT/staging environment mirroring production. | UAT/STG Environment | 2026-08-17 | 2026-10-02 |  |  | 0% |  |  | YuChung |  |  |  |  | MRSS-221
Y | 4 | 7 | 0 | Production environment provisioning 正式生產環境配置 | Provision production environment with HA/DR considerations. | PROD Environment | 2026-09-21 | 2026-10-30 |  |  | 0% |  |  | YuChung |  |  |  |  | not yet
| 4 | 8 | 0 | DR environment provisioning 災難復原環境配置 | Provision production environment with HA considerations. | DR Enviroment | 2026-08-31 | 2026-09-25 |  |  | 0% |  | 待討論 | YuChung
| 4 | 9 | 0 | Database installation & configuration 資料庫安裝與配置 | Install and configure DB; set backups and replication. | Configured Database | 2026-08-31 | 2026-10-02 |  |  | 0% |  |  | YuChung
| 4 | 10 | 0 | Security hardening & baseline configuration 安全強化與基準配置 | Apply security baseline, hardening guides, and policies. | Hardened Baseline | 2026-08-31 | 2026-10-02 |  |  | 0% |  |  | YuChung
| 4 | 11 | 0 | Logging/monitoring/audit trail setup 日誌/監控/稽核軌跡設定 | Enable centralized logs, monitoring, alerts, audit trails. | Observability Setup | 2026-08-31 | 2026-10-02 |  |  | 0% |  |  | YuChung
| 4 | 12 | 0 | Vulnerability scanning & remediation 漏洞掃描與修復 | Run scans and remediate findings. | Scan Report & Fixes | 2026-07-27 | 2026-11-30 |  |  | 0% |  |  | YuChung
| 4 | 13 | 0 | Environment readiness check 環境就緒檢查 | Validate environment readiness against checklist. | Readiness Checklist | 2026-11-01 | 2027-02-25 |  |  | 0% |  |  | YuChung
| 4 | 14 | 0 | Compliance & security validation 合規與安全性驗證 | Validate compliance/security controls and evidence. | Validation Evidence | 2026-11-01 | 2026-11-25 |  |  | 0% |  |  | YuChung
| 5 | 0 | 0 | Development 開發階段
| 5 | 1 | 0 | Sprint 1
| 5 | 1 | 1 | NM-02 ¦ 一般功能 ¦ 公告欄 |  |  | 2026-03-04 | 2026-03-31 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-Sean
| 5 | 1 | 2 | NM-03 ¦ 一般功能 ¦ 公告刊登 |  |  | 2026-03-04 | 2026-03-31 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-Sean
| 5 | 1 | 3 | NM-04 ¦ 一般功能 ¦ 便條紙 |  |  | 2026-03-18 | 2026-03-31 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-Sean
| 5 | 1 | 4 | NM-05 ¦ 一般功能 ¦ 行事曆 |  |  | 2026-03-18 | 2026-03-31 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-Sean
| 5 | 1 | 5 | MN-01 ¦ 系統管理 ¦ 組織管理 |  |  | 2026-03-04 | 2026-04-15 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-Lynn
| 5 | 1 | 6 | MN-02 ¦ 系統管理 ¦ 角色權限維護 |  |  | 2026-03-04 | 2026-04-15 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-DingYi
| 5 | 1 | 7 | MN-03 ¦ 系統管理 ¦ 人事資料維護與查詢 |  |  | 2026-03-23 | 2026-04-15 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-DingYi
| 5 | 2 | 0 | Sprint 2
| 5 | 2 | 1 | CL-01 ¦ 名單管理 ¦ 名單匯入 |  |  | 2026-04-20 | 2026-05-15 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-Jacky
| 5 | 2 | 2 | CL-02 ¦ 名單管理 ¦ 名單分派 |  |  | 2026-04-20 | 2026-04-30 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-Jacky
| 5 | 2 | 3 | CL-03 ¦ 名單管理 ¦ 名單收回與轉派 |  |  | 2026-04-08 | 2026-04-30 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-Jacky
| 5 | 2 | 4 | VID-05 ¦ 視訊招攬暨遠投作業管理 ¦ 登錄證出示 |  |  | 2026-04-08 | 2026-05-15 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-Sean
| 5 | 2 | 5 | VID-07 ¦ 視訊招攬暨遠投作業管理 ¦ 權益宣告 |  |  | 2026-04-08 | 2026-05-15 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-Sean
| 5 | 2 | 6 | MN-04 ¦ 系統管理 ¦ 職務代理 {預設} |  |  | 2026-04-08 | 2026-04-30 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-Lynn
| 5 | 3 | 0 | Sprint 3
| 5 | 3 | 1 | CMP-01 ¦ 行銷活動管理 ¦ 行銷活動查詢 |  |  | 2026-04-30 | 2026-05-31 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-DingYi
| 5 | 3 | 2 | CMP-02 ¦ 行銷活動管理 ¦ 行銷活動建立 |  |  | 2026-04-30 | 2026-05-31 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-DingYi
| 5 | 3 | 3 | CMP-03 ¦ 行銷活動管理 ¦ 行銷活動維護 |  |  | 2026-04-30 | 2026-05-31 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-DingYi
| 5 | 3 | 4 | CMP-04 ¦ 行銷活動管理 ¦ 行銷活動狀態管理 |  |  | 2026-04-30 | 2026-05-31 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-DingYi
| 5 | 3 | 5 | CMP-05 ¦ 行銷活動管理 ¦ 行銷活動管理功能 |  |  | 2026-04-30 | 2026-05-31 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-DingYi
| 5 | 3 | 6 | CL-04 ¦ 名單管理 ¦ 名單新增 |  |  | 2026-04-30 | 2026-05-29 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-Jacky
| 5 | 3 | 7 | CL-05 ¦ 名單查詢 ¦ 名單查詢 |  |  | 2026-04-30 | 2026-05-29 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-Jacky
| 5 | 3 | 8 | CRM-17 ¦ 銷售平台 ¦ 智慧名單設定 |  |  | 2026-05-18 | 2026-05-29 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-Jacky
| 5 | 3 | 9 | AS-03 ¦ 行政管理 ¦ 外發訊息查詢 |  |  | 2026-05-18 | 2026-05-29 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-Rock
| 5 | 3 | 10 | MN-05 ¦ 系統管理 ¦ 稽核軌跡查詢 |  |  | 2026-05-18 | 2026-05-29 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-Peter
| 5 | 3 | 11 | MN-04 ¦ 系統管理 ¦ 職務代理 {臨時指派} |  |  | 2026-05-18 | 2026-05-29 |  |  | 100% |  | 文件尚未sign off 僅依現有文件開發 |  | Wistron-Lynn
| 5 | 4 | 0 | Sprint 4
| 5 | 4 | 1 | VID-05 ¦ 視訊招攬暨遠投作業管理 ¦ 登錄證出示 |  |  | 2026-07-20 | 2026-08-11 |  |  | 100% |  | 根據sign off的FRS開發 |  | Wistron-Sean/ Jacky, Daniel
| 5 | 4 | 2 | VID-07 ¦ 視訊招攬暨遠投作業管理 ¦ 權益宣告 |  |  | 2026-07-20 | 2026-08-11 |  |  | 100% |  | 根據sign off的FRS開發 |  | Wistron-Sean/ Jacky, Daniel
| 5 | 4 | 3 | VID-11 ¦ 視訊招攬暨遠距投保管理 ¦ Webcall進線 |  |  | 2026-07-20 | 2026-08-11 |  |  | 100% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 4 | 4 | NM-02 ¦ 一般功能 ¦ 公告欄 |  |  | 2026-07-20 | 2026-08-11 |  |  | 100% |  | 根據sign off的FRS開發 |  | Wistron-Peter
| 5 | 4 | 5 | NM-03 ¦ 一般功能 ¦ 公告刊登 |  |  | 2026-07-20 | 2026-08-11 |  |  | 100% |  | 根據sign off的FRS開發 |  | Wistron-Peter
| 5 | 4 | 6 | NM-04 ¦ 一般功能 ¦ 便條紙 |  |  | 2026-07-20 | 2026-08-11 |  |  | 100% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 4 | 7 | NM-05 ¦ 一般功能 ¦ 行事曆 |  |  | 2026-07-20 | 2026-08-11 |  |  | 100% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 4 | 8 | MN-01 ¦ 系統管理 ¦ 組織管理 |  |  | 2026-07-20 | 2026-08-11 |  |  | 100% |  | 根據sign off的FRS開發 |  | Wistron-Lynn
| 5 | 4 | 9 | MN-02 ¦ 系統管理 ¦ 角色權限維護 |  |  | 2026-07-20 | 2026-08-11 |  |  | 100% |  | 根據sign off的FRS開發 |  | Wistron-Lynn
| 5 | 4 | 10 | MN-03 ¦ 系統管理 ¦ 人事資料維護與查詢 |  |  | 2026-07-20 | 2026-08-11 |  |  | 100% |  | 根據sign off的FRS開發 |  | Wistron-Lynn
| 5 | 4 | 11 | Epos串接確認 |  |  | 2026-07-20 | 2026-08-11 |  |  | 100% |  | 根據sign off的FRS開發 | Austin | Wistron-Daniel
| 5 | 4 | 12 | INW串接確認 |  |  | 2026-07-20 | 2026-08-11 |  |  | 100% |  | 根據sign off的FRS開發 |  | Wistron-Daniel
| 5 | 4 | 13 | Webcall串接確認 |  |  | 2026-07-20 | 2026-08-11 |  |  | 100% |  | 根據sign off的FRS開發 |  | Wistron-Daniel
| 5 | 4 | 14 | ARC-01 ¦ 平台共用 ¦ API Gateway 建置與遠投 API 路由／存取控管 |  |  | 2026-07-20 | 2026-08-11 |  |  | 50% |  | 根據sign off的FRS開發 |  | Wistron-Daniel
| 5 | 4 | 15 | SEC-01 ¦ 平台共用 ¦ 傳輸資料加解密（遠投作業） |  |  | 2026-07-20 | 2026-08-11 |  |  | 50% |  | 根據sign off的FRS開發 |  | Wistron-Daniel
| 5 | 5 | 0 | Sprint 5
| 5 | 5 | 1 | ID-01 ¦ 視訊招攬暨遠距管理功能 ¦ MID 認證 |  |  | 2026-08-12 | 2026-08-25 |  |  | 50% |  | 根據sign off的FRS開發 |  | Wistron-Sean/ Jacky, Daniel
| 5 | 5 | 2 | ID-02 ¦ 視訊招攬暨遠距管理功能 ¦ 雙軌認證 |  |  | 2026-08-12 | 2026-08-25 |  |  | 50% |  | 根據sign off的FRS開發 |  | Wistron-Sean/ Jacky, Daniel
| 5 | 5 | 3 | ID-05 ¦ 視訊招攬暨遠距管理功能 ¦ 要被保不同人 |  |  | 2026-08-12 | 2026-08-25 |  |  | 50% |  | 根據sign off的FRS開發 |  | Wistron-Sean/ Jacky, Daniel
| 5 | 5 | 4 | SIG-01 ¦ 視訊招攬暨遠距管理功能 ¦ 簽名合成 |  |  | 2026-08-12 | 2026-08-25 |  |  | 0% |  | 根據sign off的FRS開發 |  | ITRI/ Sean,Jacky
| 5 | 5 | 5 | SIG-02 ¦ 視訊招攬暨遠距管理功能 ¦ 批次套用 |  |  | 2026-08-12 | 2026-08-25 |  |  | 0% |  | 根據sign off的FRS開發 |  | ITRI/ Sean,Jacky
| 5 | 5 | 6 | SIG-03 ¦ 視訊招攬暨遠距管理功能 ¦ 文件修改 |  |  | 2026-08-12 | 2026-08-25 |  |  | 60% |  | 根據sign off的FRS開發 |  | Wistron-Sean/ Jacky, Daniel
| 5 | 5 | 7 | SIG-04 ¦ 視訊招攬暨遠距管理功能 ¦ 補充文件 |  |  | 2026-08-12 | 2026-08-25 |  |  | 40% |  | 根據sign off的FRS開發 |  | Wistron-Sean/ Jacky, Daniel
| 5 | 5 | 8 | OTHER-04 ¦ 銷售平台 ¦ 遠距照會 |  |  | 2026-08-12 | 2026-08-25 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Sean/ Jacky, Daniel
| 5 | 5 | 9 | MN-04 ¦ 系統管理 ¦ 職務代理 {預設} |  |  | 2026-08-12 | 2026-08-25 |  |  | 100% |  | 根據sign off的FRS開發 |  | Wistron-Lynn/ Ding
| 5 | 5 | 10 | MN-04 ¦ 系統管理 ¦ 職務代理 {臨時指派} |  |  | 2026-08-12 | 2026-08-25 |  |  | 100% |  | 根據sign off的FRS開發 |  | Wistron-Lynn/ Ding
| 5 | 5 | 11 | 通路串接確認 |  |  | 2026-08-12 | 2026-08-25 |  |  | 50% |  | 根據sign off的FRS開發 |  | Wistron-Daniel
| 5 | 5 | 12 | 400串接確認 |  |  | 2026-08-12 | 2026-08-25 |  |  | 50% |  | 根據sign off的FRS開發 |  | Wistron-Daniel
| 5 | 5 | 13 | Epos串接 |  |  | 2026-08-12 | 2026-08-25 |  |  | 50% |  | 根據sign off的FRS開發 |  | Wistron-Daniel
| 5 | 5 | 14 | INW串接 |  |  | 2026-08-12 | 2026-08-25 |  |  | 50% |  | 根據sign off的FRS開發 |  | Wistron-Daniel
| 5 | 6 | 0 | Sprint 6
| 5 | 6 | 1 | SIG-06 ¦ 視訊招攬暨遠距管理功能 ¦ 3份同意書 |  |  | 2026-08-26 | 2026-09-08 |  |  | 0% |  | 根據sign off的FRS開發 |  | ITRI / Sean, Jacky
| 5 | 6 | 2 | SIG-07 ¦ 視訊招攬暨遠距管理功能 ¦ 簽名框放大 |  |  | 2026-08-26 | 2026-09-08 |  |  | 0% |  | 根據sign off的FRS開發 |  | ITRI/ Sean,Jacky
| 5 | 6 | 3 | SIG-08 ¦ 視訊招攬暨遠距管理功能 ¦ 難字處理 |  |  | 2026-08-26 | 2026-09-08 |  |  | 0% |  | 根據sign off的FRS開發 |  | ITRI/ Sean,Jacky
| 5 | 6 | 4 | NM-06 ¦ 一般功能 ¦ 參數管理功能 |  |  | 2026-08-26 | 2026-09-08 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 6 | 5 | MN-05 ¦ 系統管理 ¦ 稽核軌跡查詢 |  |  | 2026-08-26 | 2026-09-08 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Peter
| 5 | 6 | 6 | MN-06 ¦ 系統管理 ¦ 系統上版設定 |  |  | 2026-08-26 | 2026-09-08 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Lynn
| 5 | 6 | 7 | MN-07 ¦ 系統管理 ¦ 匯出入作業設定 |  |  | 2026-08-26 | 2026-09-08 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-DingYi
| 5 | 6 | 8 | MN-08 ¦ 系統管理 ¦ 系統參數設定 |  |  | 2026-08-26 | 2026-09-08 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Lynn
| 5 | 6 | 9 | Audit Log/稽核軌跡 |  |  | 2026-08-26 | 2026-09-08 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Lynn
| 5 | 6 | 10 | INW影像搬移(SIT階段完成) | 2026-07-01 | 2026-07-31 | 2026-09-01 | 2026-09-30 | Wistron-Ned |  | 0% |  |  |  | Wistron-Ned
| 5 | 7 | 0 | Sprint 7
| 5 | 7 | 1 | CRM-13 ¦ 銷售平台 ¦ 客戶主檔管理 |  |  | 2026-09-09 | 2026-09-22 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 7 | 2 | CRM-18 ¦ 銷售平台 ¦ 電話外撥管理 |  |  | 2026-09-09 | 2026-09-22 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Peter
| 5 | 7 | 3 | CRM-06 ¦ 銷售平台 ¦ 電話外撥 |  |  | 2026-09-09 | 2026-09-22 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-DingYi
| 5 | 7 | 4 | CRM-10 ¦ 銷售平台 ¦ 撥打結果管理 |  |  | 2026-09-09 | 2026-09-22 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Lynn
| 5 | 7 | 5 | CRM-11 ¦ 銷售平台 ¦ 建立追蹤日誌 |  |  | 2026-09-09 | 2026-09-22 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Lynn
| 5 | 7 | 6 | CRM-12 ¦ 銷售平台 ¦ 建立約訪行程 |  |  | 2026-09-09 | 2026-09-22 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Peter
| 5 | 7 | 7 | CRM-03 ¦ 銷售平台 ¦ 保單資訊 |  |  | 2026-09-09 | 2026-09-22 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Lynn
| 5 | 7 | 8 | CRM-04 ¦ 銷售平台 ¦ 保費試算 |  |  | 2026-09-09 | 2026-09-22 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Lynn
| 5 | 7 | 9 | CRM-05 ¦ 銷售平台 ¦ 保單健檢 |  |  | 2026-09-09 | 2026-09-22 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Lynn
| 5 | 7 | 10 | CRM-14 ¦ 銷售平台 ¦ 顧客歷程 |  |  | 2026-09-09 | 2026-09-22 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-DingYi
| 5 | 7 | 11 | CRM-16 ¦ 銷售平台 ¦ SMS與 Email通用模版設定 |  |  | 2026-09-09 | 2026-09-22 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 7 | 12 | CRM-18 ¦ 銷售平台 ¦ 電話外撥管理 |  |  | 2026-09-09 | 2026-09-22 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Peter
| 5 | 7 | 13 | CMP-01 ¦ 行銷活動管理 ¦ 行銷活動查詢 |  |  | 2026-09-09 | 2026-09-22 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-DingYi
| 5 | 7 | 14 | CMP-02 ¦ 行銷活動管理 ¦ 行銷活動建立 |  |  | 2026-09-09 | 2026-09-22 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-DingYi
| 5 | 7 | 15 | CMP-03 ¦ 行銷活動管理 ¦ 行銷活動維護 |  |  | 2026-09-09 | 2026-09-22 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-DingYi
| 5 | 7 | 16 | CMP-04 ¦ 行銷活動管理 ¦ 行銷活動狀態管理 |  |  | 2026-09-09 | 2026-09-22 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Lynn
| 5 | 7 | 17 | CMP-05 ¦ 行銷活動管理 ¦ 行銷活動管理功能 |  |  | 2026-09-09 | 2026-09-22 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Lynn
| 5 | 8 | 0 | Sprint 8
| 5 | 8 | 1 | CL-01 ¦ 名單管理 ¦ 名單匯入 |  |  | 2026-09-23 | 2026-10-06 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 8 | 2 | CL-02 ¦ 名單管理 ¦ 名單分派 |  |  | 2026-09-23 | 2026-10-06 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 8 | 3 | CL-03 ¦ 名單管理 ¦ 名單收回與轉派 |  |  | 2026-09-23 | 2026-10-06 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 8 | 4 | CL-04 ¦ 名單管理 ¦ 名單新增 |  |  | 2026-09-23 | 2026-10-06 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 8 | 5 | CL-05 ¦ 名單查詢 ¦ 名單查詢 |  |  | 2026-09-23 | 2026-10-06 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 8 | 6 | CRM-17 ¦ 銷售平台 ¦ 智慧名單設定 |  |  | 2026-09-23 | 2026-10-06 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 8 | 7 | CRM-01¦ 銷售平台 ¦ 名單查詢 |  |  | 2026-09-23 | 2026-10-06 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 8 | 8 | CL-08 ¦ 名單管理 ¦ 名單分派管理 |  |  | 2026-09-23 | 2026-10-06 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Peter
| 5 | 8 | 9 | CL-09 ¦ 名單管理 ¦ 名單分派規則設定 |  |  | 2026-09-23 | 2026-10-06 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Peter
| 5 | 8 | 10 | CL-10 ¦ 名單管理 ¦ 名單清洗設定 |  |  | 2026-09-23 | 2026-10-06 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Peter
| 5 | 8 | 11 | CL-06 ¦ 名單管理 ¦ 照會名單分派 |  |  | 2026-09-23 | 2026-10-06 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 8 | 12 | CL-07 ¦名單管理 ¦ 照會覆核 |  |  | 2026-09-23 | 2026-10-06 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 8 | 13 | OTHER-02 ¦ 名單管理 ¦ 照會文件匯入 |  |  | 2026-09-23 | 2026-10-06 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Sean
| 5 | 8 | 14 | OTHER-03 ¦ 名單管理 ¦ 分批回覆 |  |  | 2026-09-23 | 2026-10-06 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Sean
| 5 | 8 | 15 | CL-12 ¦ 名單管理 ¦ AI Chatbot匯入 |  |  | 2026-09-23 | 2026-10-06 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Lynn
| 5 | 8 | 16 | CRM-02 ¦ 名單管理 ¦ 名單匯入檢核 |  |  | 2026-09-23 | 2026-10-06 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 9 | 0 | Sprint 9
| 5 | 9 | 1 | eKYC系統整合 |  |  | 2026-10-07 | 2026-10-20 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Daniel
| 5 | 9 | 2 | ID-03 ¦ 視訊招攬暨遠距管理功能 ¦ eKYC 辨識 |  |  | 2026-10-07 | 2026-10-20 |  |  | 0% |  | 根據sign off的FRS開發 |  | Vender
| 5 | 9 | 3 | ID-04 ¦ 視訊招攬暨遠距管理功能 ¦ 證件OCR |  |  | 2026-10-07 | 2026-10-20 |  |  | 0% |  | 根據sign off的FRS開發 |  | Vender
| 5 | 9 | 4 | CRM-15 ¦ 銷售平台 ¦ 文件寄送申請 |  |  | 2026-10-07 | 2026-10-20 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 9 | 5 | MN-01 ¦ 文件管理 ¦ 話術管理 |  |  | 2026-10-07 | 2026-10-20 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Peter
| 5 | 9 | 6 | MN-02 ¦ 文件管理 ¦ 文件管理 |  |  | 2026-10-07 | 2026-10-20 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Peter
| 5 | 9 | 7 | AS-03 ¦ 行政管理 ¦ 外發訊息查詢 |  |  | 2026-10-07 | 2026-10-20 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Lynn
| 5 | 9 | 8 | AS-04 ¦ 行政管理 ¦ 客服轉三方通話功能 |  |  | 2026-10-07 | 2026-10-20 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 9 | 9 | AS-01 ¦ 行政管理 ¦ 文件寄送作業 |  |  | 2026-10-07 | 2026-10-20 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Peter
| 5 | 9 | 10 | AS-02 ¦ 行政管理 ¦ 行政工作佇列 |  |  | 2026-10-07 | 2026-10-20 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Peter
| 5 | 10 | 0 | Sprint 10
| 5 | 10 | 1 | RP-01 ¦ 報表管理 ¦ 名單控管表 |  |  | 2026-10-21 | 2026-11-03 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-DingYi
| 5 | 10 | 2 | RP-02 ¦ 報表管理 ¦ 每日績效表 |  |  | 2026-10-21 | 2026-11-03 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 10 | 3 | RP-03 ¦ 報表管理 ¦ 通時報表 |  |  | 2026-10-21 | 2026-11-03 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Lynn
| 5 | 10 | 4 | RP-04 ¦ 報表管理 ¦ KPI報表 |  |  | 2026-10-21 | 2026-11-03 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Peter
| 5 | 10 | 5 | RP-05 ¦ 報表管理 ¦ Term Code報表 |  |  | 2026-10-21 | 2026-11-03 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 10 | 6 | RP-06 ¦ 報表管理 ¦ 業績報表 |  |  | 2026-10-21 | 2026-11-03 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Sean
| 5 | 10 | 7 | RP-07 ¦ 報表管理 ¦ 名單分派統計表 |  |  | 2026-10-21 | 2026-11-03 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-DingYi
| 5 | 10 | 8 | RP-08 ¦ 報表管理 ¦ Campaign報表 |  |  | 2026-10-21 | 2026-11-03 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Jacky
| 5 | 10 | 9 | RP-09 ¦ 報表管理 ¦ 每日綜合報表 |  |  | 2026-10-21 | 2026-11-03 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Lynn
| 5 | 10 | 10 | RP-10 ¦ 報表管理 ¦ 出缺勤紀錄 |  |  | 2026-10-21 | 2026-11-03 |  |  | 0% |  | 根據sign off的FRS開發 |  | Wistron-Peter
| 6 | 0 | 0 | Testing & QA 測試與品質保證
| 6 | 1 | 0 | SIT 1 - 遠距投保, 視訊銷售招攬,一般功能
| 6 | 1 | 1 | SIT測試計畫與案例 |  |  | 2026-08-10 | 2026-08-31 |  |  | 40% |  |  | Kathy | Wistron-Ned
Y | 6 | 1 | 2 | SIT test |  |  | 2026-09-23 | 2026-10-16 |  |  | 0% |  |  |  | Wistron-Ned
| 6 | 2 | 0 | SIT 2 - 名單管理, 外撥系統,行政
| 6 | 2 | 1 | SIT測試計畫與案例 |  |  | 2026-09-01 | 2026-09-15 |  |  | 0% |  |  | Kathy | Wistron-Ned
Y | 6 | 2 | 2 | SIT test |  |  | 2026-11-06 | 2026-11-30 |  |  | 0% |  |  |  | Wistron-Ned
| 6 | 3 | 0 | UAT1
| 6 | 3 | 1 | UAT測試計畫與案例 |  |  | 2026-08-25 | 2026-09-18 |  |  | 0% |  |  | Linda
Y | 6 | 3 | 2 | UAT test - Round 1 |  |  | 2026-09-30 | 2026-12-01 |  |  | 0% |  |  | Linda
| 6 | 3 | 3 | UAT結果與反饋修正 |  |  | 2026-10-01 | 2026-12-01 |  |  | 0% |  |  | Linda
| 6 | 4 | 0 | UAT2
| 6 | 4 | 1 | UAT測試計畫與案例 |  |  | 2026-09-19 | 2026-09-29 |  |  | 0% |  |  | Linda
Y | 6 | 4 | 2 | UAT test - Round 2 |  |  | 2026-11-16 | 2027-02-16 |  |  | 0% |  |  | Linda
| 6 | 4 | 3 | UAT結果與反饋修正 |  |  | 2027-02-17 | 2027-02-28 |  |  | 0% |  |  | Linda
| 6 | 5 | 0 | 非功能測試
| 6 | 5 | 1 | Performance - Performance Test |  |  | 2026-11-09 | 2026-11-30 |  |  | 0% |  |  | YuChung
| 6 | 5 | 2 | Reliability - Resiliency Test |  |  | 2026-11-09 | 2026-11-30 |  |  | 0% |  |  | YuChung
| 6 | 5 | 3 | Security - 黑箱測試 |  |  | 2026-11-09 | 2026-11-30 |  |  | 0% |  |  | YuChung
| 6 | 5 | 4 | API Security 掃描 |  |  | 2026-11-16 | 2026-12-10 |  |  | 0% |  |  | YuChung
| 6 | 5 | 5 | Operation - Operational Readiness Test |  |  | 2026-11-09 | 2026-12-11 |  |  | 0% |  |  | YuChung
| 7 | 0 | 0 | Deployment & Release Management 部屬與發佈管理 Phase 1
| 7 | 1 | 1 | Phase 1
| 7 | 2 | 1 | Implementaion Planing 實施/執行計畫規劃 | Plan deployment steps, rollback, communications. | Implemention Plan / Runbook | 2026-09-02 | 2026-10-04 |  |  | 0% |  |  |  | Wistron-Ned
| 7 | 3 | 1 | Deployment Runbook |  |  | 2026-11-15 | 2026-11-30 |  |  | 0% |  |  |  | Wistron-Ned
| 7 | 4 | 1 | Rollback Plan |  |  | 2026-11-15 | 2026-11-30 |  |  | 0% |  |  |  | Wistron-Ned
| 7 | 5 | 1 | Communication Plan |  |  | 2026-11-15 | 2026-11-30 |  |  | 0% |  |  |  | Wistron-Ned
| 7 | 6 | 1 | Production deployment 正式環境部屬 | Execute production deployment and configuration. | Deployed Release | 2026-11-01 | 2026-11-30 |  |  | 0% |  |  | YuChung
| 7 | 7 | 1 | Release readiness review 發布就緒審查 | Review release checklist, risks, approvals. | Readiness Review | 2026-12-01 | 2026-12-10 |  |  | 0% |  |  |  | Wistron-Ned
| 7 | 8 | 1 | Infra readiness |  |  | 2026-12-01 | 2026-12-10 |  |  | 0% |  |  |  | Wistron-Ned
| 7 | 9 | 1 | App readiness |  |  | 2026-12-01 | 2026-12-10 |  |  | 0% |  |  |  | Wistron-Ned
| 7 | 10 | 1 | Data readiness |  |  | 2026-12-01 | 2026-12-10 |  |  | 0% |  |  |  | Wistron-Ned
| 7 | 11 | 1 | Security readiness |  |  | 2026-12-01 | 2026-12-10 |  |  | 0% |  |  |  | Wistron-Ned
Y | 7 | 12 | 1 | GO or No Go Meeting 上線決策會議 | A Meeting with Senior about Go/No Go | Go/No-Go Decision | 2026-12-11 | 2026-12-17 |  |  | 0% |  |  | Kathy
Y | 7 | 13 | 1 | Release / Launch 發佈/上線 | Launch Date | App Go-Live | 2026-12-26 | 2026-12-26 |  |  | 0% |  |  | YuChung
| 7 | 14 | 1 | Post-deployment validation 部屬後驗證 | Validate smoke tests and monitoring post go-live. | Post-GoLive Validation | 2027-01-01 | 2027-01-02 |  |  | 0% |  |  | YuChung
| 7 | 15 | 1 | Post-implementation review 實署後審查 | Review of Deployment Issue | PIR Meeting | 2027-01-03 | 2027-01-05 |  |  | 0% |  |  | YuChung
| 8 | 0 | 0 | Deployment & Release Management 部屬與發佈管理 Phase 2
| 8 | 1 | 1 | Implementaion Planing 實施/執行計畫規劃 | Plan deployment steps, rollback, communications. | Implemention Plan / Runbook | 2027-01-10 | 2027-01-15 |  |  | 0% |  |  |  | Wistron-Ned
| 8 | 2 | 1 | Deployment Runbook |  |  | 2027-01-15 | 2027-01-30 |  |  | 0% |  |  |  | Wistron-Ned
| 8 | 3 | 1 | Rollback Plan |  |  | 2027-02-15 | 2027-02-27 |  |  | 0% |  |  |  | Wistron-Ned
| 8 | 4 | 1 | Communication Plan |  |  | 2027-02-15 | 2027-02-27 |  |  | 0% |  |  |  | Wistron-Ned
| 8 | 5 | 1 | Production deployment 正式環境部屬 | Execute production deployment and configuration. | Deployed Release | 2027-02-15 | 2027-02-27 |  |  | 0% |  |  | YuChung
| 8 | 6 | 1 | Release readiness review 發布就緒審查 | Review release checklist, risks, approvals. | Readiness Review | 2027-03-01 | 2027-03-10 |  |  | 0% |  |  |  | Wistron-Ned
| 8 | 7 | 1 | Infra readiness |  |  | 2027-03-01 | 2027-03-10 |  |  | 0% |  |  |  | Wistron-Ned
| 8 | 8 | 1 | App readiness |  |  | 2027-03-01 | 2027-03-10 |  |  | 0% |  |  |  | Wistron-Ned
| 8 | 9 | 1 | Data readiness |  |  | 2027-03-01 | 2027-03-10 |  |  | 0% |  |  |  | Wistron-Ned
| 8 | 10 | 1 | Security readiness |  |  | 2027-03-01 | 2027-03-10 |  |  | 0% |  |  |  | Wistron-Ned
| 8 | 11 | 1 | GO or No Go Meeting 上線決策會議 | A Meeting with Senior about Go/No Go | Go/No-Go Decision | 2027-03-11 | 2027-03-15 |  |  | 0% |  |  | Kathy
| 8 | 12 | 1 | Release / Launch 發佈/上線 | Launch Date | App Go-Live | 2027-03-26 | 2027-03-26 |  |  | 0% |  |  | YuChung
| 8 | 13 | 1 | Post-deployment validation 部屬後驗證 | Validate smoke tests and monitoring post go-live. | Post-GoLive Validation | 2027-03-27 | 2027-03-28 |  |  | 0% |  |  | YuChung
| 8 | 14 | 1 | Post-implementation review 實署後審查 | Review of Deployment Issue | PIR Meeting | 2027-03-29 | 2027-03-31 |  |  | 0% |  |  | YuChung
Y | 9 | 0 | 0 | Data Migration & Cut-over / Go-live Readiness 資料轉移與上線切換規劃 |  |  | 2026-08-14 | 2026-12-25 |  |  | 0% |  |  |  | Wistron-Ned
| 9 | 1 | 1 | Data Inventory & Scoping 資料盤點 |  |  | 2026-08-14 | 2026-09-14 |  |  | 0% |  |  |  | Wistron-Ned
| 9 | 2 | 1 | Data Quality & Cleansing Assessment 資料品質評估 |  |  | 2026-09-30 | 2026-10-14 |  |  | 0% |  |  |  | Wistron-Ned
| 9 | 3 | 1 | Data Mapping & Transformation 資料對應設計 |  |  | 2026-08-30 | 2026-09-30 |  |  | 0% |  |  |  | Wistron-Ned
| 9 | 4 | 1 | TMPRO data migration 合約 |  |  | 2026-09-01 | 2026-10-31 |  |  | 0%
| 9 | 5 | 1 | Migration Strategy & Cutover 移轉策略 |  |  | 2026-08-14 | 2026-09-14 |  |  | 0% |  |  |  | Wistron-Ned
| 9 | 6 | 1 | Dry Run & Readiness Validation 試轉移驗證 SIT |  |  | 2026-12-01 | 2026-12-15 |  |  | 0% |  |  |  | Wistron-Ned
| 9 | 7 | 1 | Data Extraction 資料抽取 |  |  | 2026-12-01 | 2026-12-15 |  |  | 0% |  |  |  | Wistron-Ned
| 9 | 8 | 1 | Data Load 資料匯入 |  |  | 2026-12-01 | 2026-12-15 |  |  | 0%
| 9 | 9 | 1 | Data Validation & Reconciliation 資料比對驗證 |  |  | 2026-12-01 | 2026-12-25 |  |  | 0% |  |  |  | Wistron-Ned
| 9 | 10 | 1 | Dry Run & Readiness Validation 試轉移驗證 UAT |  |  | 2027-01-01 | 2027-01-15 |  |  | 0% |  |  |  | Wistron-Ned
| 9 | 11 | 1 | Data Extraction 資料抽取 |  |  | 2027-01-01 | 2027-01-15 |  |  | 0% |  |  |  | Wistron-Ned
| 9 | 12 | 1 | Data Load 資料匯入 |  |  | 2027-01-01 | 2027-01-15 |  |  | 0%
| 9 | 13 | 1 | Data Validation & Reconciliation 資料比對驗證 |  |  | 2027-01-01 | 2027-01-15 |  |  | 0% |  |  |  | Wistron-Ned
| 9 | 14 | 1 | Production deployment 正式環境部屬 | Execute production deployment and configuration. | Deployed Release | 2027-03-01 | 2027-03-15 |  |  | 0% |  |  | YuChung
| 9 | 15 | 1 | Release approval & go-live confirmation 發佈核准予上線確認 | Formal approval for go-live. | Go-live Approval | 2027-03-16 | 2027-03-16 |  |  | 0% |  |  | YuChung
Y | 9 | 16 | 1 | Release / Launch 發佈/上線 | Launch Date | App Go-Live | 2027-03-26 | 2027-03-26 |  |  | 0% |  |  | YuChung
| 9 | 17 | 1 | Post-deployment validation 部屬後驗證 | Validate smoke tests and monitoring post go-live. | Post-GoLive Validation | 2027-03-29 | 2027-03-29 |  |  | 0% |  |  | YuChung
| 9 | 18 | 1 | Post-implementation review 實署後審查 | Review of Deployment Issue | PIR Meeting | 2027-03-30 | 2027-03-30 |  |  | 0% |  |  | YuChung
| 10 | 0 | 0 | Doc and Knowledge Transfer 文件與知識轉移
| 10 | 1 | 1 | Operations & maintenance manual 維運手冊 | Prepare O&M manual, SOPs. | O&M Manual | 2027-02-01 | 2027-02-20 |  |  | 0% |  |  |  | Wistron-Ned
| 10 | 2 | 1 | Security & compliance documentation 安全與合規文件 | Prepare evidence, control descriptions, audit artifacts. | Compliance Pack | 2027-02-01 | 2027-02-20 |  |  | 0% |  |  |  | Wistron-Ned
| 10 | 3 | 1 | User guides & training materials 使用者指南與培訓教材 | Prepare user guides and training materials. | User Guide/Training | 2027-02-01 | 2027-02-20 |  |  | 0% |  |  |  | Wistron-Ned
| 10 | 4 | 1 | Knowledge transfer to operations 維運知識轉移 | Conduct KT sessions and handover walkthrough. | KT Completion | 2027-02-01 | 2027-02-20 |  |  | 0% |  |  |  | Wistron-Ned
| 11 | 0 | 0 | Operations Readiness & Handover 維運準備與交接
| 11 | 1 | 1 | AP後續維運討論 |  |  | 2026-09-14 | 2027-10-22 |  |  | 0% |  |  | Kathy
| 11 | 2 | 1 | Operational readiness assessment 維運就緒程度評估 | Assess readiness: monitoring, support, SLAs. | Ops Readiness Report | 2026-09-30 | 2026-12-10 |  |  | 0% |  |  | YuChung
| 11 | 3 | 1 | Incident & change management alignment 事件與變更管理流程一致化 | Align incident/change processes and workflows. | ITSM Alignment | 2026-09-30 | 2026-12-10 |  |  | 0% |  |  | YuChung
| 11 | 4 | 1 | Backup & DR validation 備份與災難恢復驗證 | Validate backup/restore and DR drills. | Backup/DR Evidence | 2026-09-30 | 2026-12-10 |  |  | 0% |  | 待討論 | YuChung
Y | 11 | 5 | 1 | Formal handover to operations 正式交接維運團隊 | Complete handover and acceptance. | Handover Sign-off | 2027-04-01 | 2027-04-01 |  |  | 0% |  |  | Thomas
| 11 | 6 | 1 | ISO27001擴大驗證 |  |  | 2027-02-01 | 2027-04-26 |  |  | 0% |  |  | Kathy